## Read me
Conditional Access Baseline Kit: Top 5
Version | 1.0 (2026-10-28; facts re-read on Microsoft Learn 2026-10-28; validated: quality gate, read-only guard, PowerShell 7.4 parse, Excel recalc)
What this is | The same backlog as the Jira CSV, as a project plan for teams without Jira. One row per control on 'Project plan'; 'Dashboard' shows progress.
Your cells | Yellow cells on 'Project plan': Owner, Start, Due, Status, Done date, Notes. Everything else is filled in or calculated.
Status values | To do, In progress, Blocked, Done, Not applicable. Pick from the drop-down.
% complete | Done = 100%. In progress = 50% (assumption: a simple midpoint, so the dashboard moves before a control is finished). Everything else = 0%. 'Not applicable' rows are left out of the totals.
Effort (h) | Hands-on hours from the guide: upper end of a range, minutes converted to hours. Waiting time (DNS, rollout weeks, recurring reviews) is not included.
Overdue | Due date before today and status not Done or Not applicable.
Example row | Owner: j.doe · Start: 03/11/2026 · Due: 07/11/2026 · Status: In progress · Done date: (empty until Done) · Notes: Report-only since 03/11, review on 06/11.
Details per control | Why, steps, read-only check, verify, licence and sources are in the guide (.md) that ships in the same zip.
Disclaimer | Not affiliated with or endorsed by Microsoft. Test every change in Report-only or on a pilot group first.

## Dashboard
Conditional Access Baseline Kit: Top 5 — progress
All figures are formulas over 'Project plan'. 'Not applicable' rows are excluded from % complete.
By area
Area | Controls | Done | In progress | Blocked | Not applicable | % complete | Overdue | Hours left
Foundation and emergency access
Strong authentication for everyone
Block weak sign-in paths
Total
By sprint
Sprint | Controls | Done | In progress | Blocked | Not applicable | % complete | Overdue | Hours left
Sprint 1 - Foundation
Sprint 2 - Enforce MFA and block legacy
Total

## Project plan
ID | Control | Area | Sprint | Priority | Effort (guide) | Effort (h) | Licence | Owner | Start | Due | Status | Done date | % complete | Overdue | Verify (done when…) | Notes
CA01 | Create two emergency access accounts, exclude them from every policy and alert on their use | Foundation and emergency access | Sprint 1 - Foundation | Highest | 2 h | 2 | Accounts: any edition. Alert rule: Azure Monitor / Log Analytics (pay-as-you-go ingestion, usually small). |  |  |  | To do |  |  |  | Two emergency accounts exist with phishing-resistant credentials; every active policy that blocks or restricts excludes them; a test sign-in raised the alert within minutes.
CA02 | Name policies by persona and create every new policy in Report-only first | Foundation and emergency access | Sprint 1 - Foundation | Highest | 1 h | 1 | Microsoft Entra ID P1 (included in Microsoft 365 Business Premium, E3 and E5). |  |  |  | To do |  |  |  | Every policy follows the naming convention; new policies show state 'enabledForReportingButNotEnforced' for at least 7 days before 'enabled'.
CA03 | Require MFA for all users on all resources with an authentication strength | Strong authentication for everyone | Sprint 2 - Enforce MFA and block legacy | Highest | 2 h + 7 days report-only | 2 | Microsoft Entra ID P1 (included in Microsoft 365 Business Premium, E3 and E5). Authentication strengths need P1. |  |  |  | To do |  |  |  | One policy with All users + All resources + an authentication strength is On; the sign-in logs show no unexpected failures for 7 days.
CA04 | Block legacy authentication for all users | Block weak sign-in paths | Sprint 2 - Enforce MFA and block legacy | Highest | 1 h + 7 days report-only | 1 | Microsoft Entra ID P1 (included in Microsoft 365 Business Premium, E3 and E5). |  |  |  | To do |  |  |  | A legacy-auth block policy is On; the sign-in logs show no successful sign-ins with Exchange ActiveSync or Other clients.
CA05 | Require phishing-resistant MFA for administrators | Strong authentication for everyone | Sprint 2 - Enforce MFA and block legacy | Highest | 2 h + 7 days report-only | 2 | Microsoft Entra ID P1 (included in Microsoft 365 Business Premium, E3 and E5). Passkeys (FIDO2) are available in all editions. |  |  |  | To do |  |  |  | A policy with the Phishing-resistant MFA strength covers at least the 14 recommended roles and is On; every admin shows a passkey, FIDO2 or Windows Hello method.
Formulas:
Overdue = IF(AND(ISNUMBER([Due]),[Due]<TODAY(),[Status]<>"Done",[Status]<>"Not applicable"),"Yes","")